## Read Me
MI MARKET INTELLIGENCE TOOLS · marketintelligencetools.com/templates/
Feasibility Analysis Template
Read this tab first. Italic rows on every tab are the worked example (Larkfield Software); overwrite them with your own project.
TOPIC | HOW IT WORKS
What this file does | Scores a proposed project on five feasibility dimensions (market, technical, financial, operational, legal), runs the NPV, payback and sensitivity math, and logs risks and assumptions.
Tab order | Read Me > Project Overview > Scorecard > Financials > Sensitivity > Risks > Assumptions. The verdict comes first; the evidence behind it follows.
Step 1 | Project Overview: name the project, scope, sponsor, objectives, kill criteria and decision date. Write the no-go line before any data comes in.
Step 2 | Agree the five weights on the Scorecard tab with the approver before scoring. Weights must total 100%.
Step 3 | Financials: enter price, cost assumptions, discount rate, initial investment and accounts per year. NPV, payback and ROI calculate.
Step 4 | Sensitivity: each row moves one input at a time against the base case. The combined row is a stress test only.
Step 5 | Risks: score likelihood and impact from 1 to 5. Score = likelihood x impact. Anything at 12 or above needs a named mitigation before approval.
Step 6 | Score each dimension from 1 to 5 on the Scorecard and write one sentence of evidence per score. The verdict calculates.
Scoring scale | 1 = serious doubt, 2 = weak, 3 = workable with conditions, 4 = strong, 5 = proven by evidence.
Verdict thresholds | Weighted total of 3.75 and up = Go. 3.00 to 3.74 = Conditional go. Under 3.00 = No-go.
NPV formula
Companion file | feasibility-study-report-template.docx presents these findings in nine sections. Paste final figures into it once the numbers stop moving.

## Project Overview
MI MARKET INTELLIGENCE TOOLS · marketintelligencetools.com/templates/
Project Overview
Two sentences per field at most. Write the kill criteria before gathering data, so the analysis has a no-go line to test against.
FIELD | DETAIL
Project name | Larkfield self-serve agency tier
Company | Larkfield Software (fictional): 45 people, reporting tool for mid-size marketing teams at $299 a month
Proposed project | A $49-a-month self-serve tier for agencies with fewer than 20 staff, a new product line
Scope | Self-serve onboarding flow and card billing, reusing the existing reporting engine; tier capped at three seats
Problem it solves | Small agencies need the reporting but can't justify the $299 plan
Sponsor / approver | CEO (approver); head of product (sponsor)
Initial investment | $180,000: $120,000 build, $25,000 billing, tax and compliance setup, $35,000 launch marketing
Revenue objective | $588,000 revenue in year 3
Adoption objective | 1,000 average paying accounts in year 3
Kill criteria | Fewer than 100 paying accounts at the end of a 90-day pilot; NPV at 10% below zero on the base case
Hurdle rate | 10% discount rate
Decision date | Approval meeting at the end of the feasibility study
Verdict | Conditional go: release the $35,000 launch budget only after the pilot reaches 100 paying accounts

## Scorecard
MI MARKET INTELLIGENCE TOOLS · marketintelligencetools.com/templates/
Feasibility Scorecard
Agree the weights with the approver first. Score 1 to 5 and back every score with one sentence of evidence. Weighted = weight x score.
DIMENSION | QUESTION IT ANSWERS | WEIGHT | SCORE (1-5) | WEIGHTED | EVIDENCE / RATIONALE
Market | Is there customer demand at the planned price? | 30% | 4 |  | Rivals charge $39 to $79; 14 of 20 agencies interviewed named the reporting pain unprompted
Technical | Can the team build it with the resources and time available? | 20% | 4 |  | Onboarding reuses the existing reporting engine; four-month build
Financial | Is the project viable, with a return that beats the cost of capital? | 25% | 3 |  | NPV of $53,858 turns negative on a 9% demand miss
Operational | Can the organization run it after launch? | 15% | 3 |  | Needs one support hire; no help centre yet
Legal | Can it run lawfully in every market you plan to sell in? | 10% | 4 |  | Card billing in two countries needs VAT and sales-tax compliance
Total
Verdict
Thresholds | 3.75 and up = Go · 3.00 to 3.74 = Conditional go · under 3.00 = No-go
Condition | A 90-day pilot must reach 100 paying accounts before the $35,000 of launch funding is released.

## Financials
MI MARKET INTELLIGENCE TOOLS · marketintelligencetools.com/templates/
Financials
Edit the inputs in rows 6-12 and the accounts in row 16. Everything else calculates. Year 0 sits outside NPV().
ASSUMPTION | VALUE
Price per account per month | 49
Variable costs (% of revenue) | 30%
Fixed costs per year | 150000
Discount rate (hurdle) | 10%
Investment: build | 120000
Investment: billing, tax and compliance setup | 25000
Investment: launch marketing | 35000
Initial investment (Year 0)
LINE | YEAR 0 | YEAR 1 | YEAR 2 | YEAR 3
Average paying accounts |  | 250 | 600 | 1000
Revenue ($49 x 12 per account)
Variable costs (30%)
Fixed costs
Initial investment
Net cash flow
Cumulative cash flow
RESULT | VALUE
NPV at discount rate
Payback period
Three-year cumulative net
Return on investment (3 years)
Hurdle rate

## Sensitivity
MI MARKET INTELLIGENCE TOOLS · marketintelligencetools.com/templates/
Sensitivity Analysis
Move one input per row against the base case. Columns C-E hold the moved inputs; the combined row exists only as a stress test.
SCENARIO | CHANGE | DEMAND X | PRICE / MONTH | FIXED / YEAR | NET Y0 | NET Y1 | NET Y2 | NET Y3 | NPV AT RATE | PAYBACK
Base case | None | 100%
Demand -20% | 200 / 480 / 800 accounts | 80%
Price -10% | $44 a month | 100% | 44
Fixed costs +15% | $172,500 a year | 100%
Combined downside | Demand -20% and fixed costs +15% | 80%
Break-even demand |  | Share of planned demand at which base-case NPV reaches zero. Worked example: 91.1%, so a shortfall of just under 9% wipes out the return.

## Risks
MI MARKET INTELLIGENCE TOOLS · marketintelligencetools.com/templates/
Risk Register
Score likelihood and impact from 1 to 5. Score = likelihood x impact. Anything at 12 or above needs a named mitigation before project approval.
RISK | DIMENSION | LIKELIHOOD (1-5) | IMPACT (1-5) | SCORE | MITIGATION | OWNER
Demand below plan in year one | Market | 3 | 4 |  | 90-day pilot gate of 100 paying accounts before launch spend | Head of product
Support load outgrows one hire | Operational | 3 | 3 |  | Help centre and in-app guides built before launch | Support lead
Cannibalises the $299 tier | Financial | 2 | 4 |  | Cap the self-serve tier at three seats | Head of product
VAT and sales tax in two countries | Legal | 2 | 3 |  | Bill through a merchant-of-record provider | Finance lead
Onboarding build overruns four months | Technical | 3 | 2 |  | Fixed-scope first release; cut features before moving dates | Engineering lead

## Assumptions
MI MARKET INTELLIGENCE TOOLS · marketintelligencetools.com/templates/
Assumptions Log
One row per number the verdict depends on. Low-confidence rows are the ones the pilot or the sensitivity tab has to test.
KEY ASSUMPTION | SOURCE | CONFIDENCE | HOW TO TEST IT
250 / 600 / 1,000 average paying accounts in years 1-3 | Bottom-up count of reachable agencies; 14 of 20 interviewed named the pain | Low | 90-day pilot: 100 paying accounts is the gate
Price of $49 a month | Rival pricing of $39 to $79 | Medium | Pilot conversion at $49; Price -10% row on the Sensitivity tab
Variable costs at 30% of revenue | Current hosting, payment and support cost per account | Medium | Recheck after three pilot billing cycles
Fixed costs of $150,000 a year | One support hire plus tier maintenance | Medium | Fixed costs +15% row on the Sensitivity tab
$120,000 build in four months | Engineering estimate; onboarding reuses the existing reporting engine | High | Fixed-scope first release; milestone review at month two
10% discount rate | Company hurdle rate | High | Confirm with finance before approval